## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Description | Completed Checklist Items | Checklist Items | Labels
--241aSc00GnHbGn30-nzskAGR3k | Define project scope and boundaries | Initiating | Completed | Medium | MALSHAN W A D D I it22137050 | MALSHAN W A D D I it22137050 | 11/27/2025 |  |  | false | false | 01/06/2026 | MALSHAN W A D D I it22137050
5npBe7rrFEiHQJ3YD5FF5ckADUs1 | Select Suitable Sensors (Camera, Temp, Humidity) | Planning | Completed | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 11/19/2025 | 12/06/2025 | false | false | 12/15/2025 | WEERAWARDANE K W R C it22239402 | Choose camera and environmental sensors from Pettah.
78SZjY4NekqYq-PE0pJSNskAM4ph | Installed Python 3.11 manually alongside Python 3.13 | Executing | Completed | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 01/02/2026 | 12/29/2025 | 12/29/2025 | false | false | 01/02/2026 | WEERAWARDANE K W R C it22239402
8-n6xvdCcU-9N4Fkv7__8MkAJA2A | Validate UI usability | Monitoring and controlling | Completed | Medium | MALSHAN W A D D I it22137050 | MALSHAN W A D D I it22137050 | 11/27/2025 |  |  | false | false | 01/06/2026 | MALSHAN W A D D I it22137050
8OTuNIpjckmIiVOC9AyLVckABRiT | Conduct a literature review and identify research gap | Initiating | Completed | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 11/27/2025 |  |  | false | false | 01/06/2026 | UDAWELA U.K.R.M.R.N. it22271396
9KRjfQvEZ0eLfrezuiK6wskALppg | Adjust fertilization algorithm | Monitoring and controlling | Completed | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 11/27/2025 |  | 01/01/2026 | false | false | 01/06/2026 | UDAWELA U.K.R.M.R.N. it22271396
AxE8MhjzIEuO0tpb9yhwL8kAJgOA | UI/UX implementation | Planning | Completed | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 12/09/2025 | 01/01/2026 | false | false | 01/11/2026 | WEERAWARDANE K W R C it22239402
CBIsfD6QOES0wHLK4IqpVMkAAH3a | Improve dataset if misclassifications appear | Monitoring and controlling | Completed | Medium | MALSHAN W A D D I it22137050 | MALSHAN W A D D I it22137050 | 11/27/2025 |  |  | false | false | 01/06/2026 | MALSHAN W A D D I it22137050
DWkgdDunz0eQ7VJQzxb16skALMUQ | Collect tea leaf image dataset | Executing | Completed | Medium | MALSHAN W A D D I it22137050 | MALSHAN W A D D I it22137050 | 11/27/2025 |  |  | false | false | 01/06/2026 | MALSHAN W A D D I it22137050
DXPLe0FGNUO_lzGi9h4iBckAKQaA | Create wireframes using Figma | Planning | Completed | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 11/19/2025 | 12/15/2025 | false | false | 12/22/2025 | WEERAWARDANE K W R C it22239402
FXLUB10MpkGcw_DUXfY9-skAMemp | Research CNN Architectures | Planning | Completed | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 11/19/2025 | 11/20/2025 | false | false | 11/27/2025 | WEERAWARDANE K W R C it22239402 | Evaluate various CNN architectures.
Ffbqyxpo4EyjG6VlCKqEdskAE9ib | UI/UX design | Planning | Completed | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 11/27/2025 |  | 12/10/2025 | false | false | 01/06/2026 | UDAWELA U.K.R.M.R.N. it22271396
GfTn8WCsfUWJHZe3LigUEMkAMNM- | Conduct Literature Survey on AI-Based Tea Grading | Initiating | Completed | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 08/10/2025 | 08/10/2025 | false | false | 11/19/2025 | WEERAWARDANE K W R C it22239402 | Review publications on AI and IoT in agriculture
I1Wee4adqEyRBf1Prybf18kAFfdN | Choose technologies (YOLOv10, Android APIs, Cloud) | Planning | Completed | Medium | MALSHAN W A D D I it22137050 | MALSHAN W A D D I it22137050 | 11/27/2025 |  |  | false | false | 01/06/2026 | MALSHAN W A D D I it22137050
J86tR6gfqU6GMXMyaxsr98kAIloV | Identify knowledge gap between Red Rust and Potassium Deficiency | Initiating | Completed | Medium | MALSHAN W A D D I it22137050 | MALSHAN W A D D I it22137050 | 11/27/2025 |  |  | false | false | 01/06/2026 | MALSHAN W A D D I it22137050
KYsYpUWEsEiFXN0GNieCHckANtQs | Selected Raspberry Pi 4 as main controller and Selected sensors | Planning | Completed | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 01/02/2026 | 11/05/2025 | 12/17/2025 | false | false | 01/02/2026 | WEERAWARDANE K W R C it22239402 | Selected Raspberry Pi 4 as main controller Selected sensors (DHT22, MQ135, BH1750 – optional)
MvvKZ-D-4k2n-m3KEAvwv8kAAWN9 | Finalize Research Scope and Problem | Initiating | Completed | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 08/10/2025 | 08/10/2025 | false | false | 11/19/2025 | WEERAWARDANE K W R C it22239402 | Define scope and finalize problem statement.
Ngf2miunCUCgg9xXolIZ7skADV4A | System architecture design | Planning | Completed | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 11/27/2025 |  | 12/25/2025 | false | false | 01/06/2026 | UDAWELA U.K.R.M.R.N. it22271396
QIaeQuVtHUKph_Yiq7-N6MkALcTL | Monitored sensor reading stability | Monitoring and controlling | Completed | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 01/02/2026 | 12/30/2025 | 12/30/2025 | false | false | 01/02/2026 | WEERAWARDANE K W R C it22239402
R4ch_67mv0iG0QEXLJlWHMkAClIj | Identify AI & IoT Requirements | Initiating | Completed | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 09/10/2025 | 09/10/2025 | false | false | 11/19/2025 | WEERAWARDANE K W R C it22239402 | Identify functional and technical requirements.
RbQVWQ12K06jz0BdcDXnRckAB9aA | Select Hardware (ESP32 / Raspberry Pi) | Planning | Completed | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 11/19/2025 | 12/06/2025 | false | false | 12/15/2025 | WEERAWARDANE K W R C it22239402 | Choose microcontroller
S0pHI7KwNEqq6T3RRmS568kAEAe1 | Identify project risks (image quality, overlapping symptoms) | Planning | Completed | Medium | MALSHAN W A D D I it22137050 | MALSHAN W A D D I it22137050 | 11/27/2025 |  |  | false | false | 01/06/2026 | MALSHAN W A D D I it22137050
SK7uZIy6dE6BI3mSfumFF8kACEAA | Implement disease suggestion module | Executing | Completed | Medium | MALSHAN W A D D I it22137050 | MALSHAN W A D D I it22137050 | 11/27/2025 |  |  | false | false | 01/06/2026 | MALSHAN W A D D I it22137050
T2Oy0sz5CUuajVXeBpHBcskAJ9IS | Hardware and software selection | Planning | Completed | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 11/27/2025 |  |  | false | false | 01/06/2026 | UDAWELA U.K.R.M.R.N. it22271396
Tmnwv3LgA0uCOsz9JrZ3AMkAIutx | Plan and Schedule Field Visit for Tea Image Capture | Planning | Completed | Medium | MALSHAN W A D D I it22137050;WEERAWARDANE K W R C it22239402;UDAWELA U.K.R.M.R.N. it22271396;JAYASUNDARA K.B.S.M it22241832 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 11/21/2025 | 11/28/2025 | false | false | 12/15/2025 | WEERAWARDANE K W R C it22239402 | Plan date and schedule for field visit.
UXBCR5eaB0KghugYjC0iaMkAHXFZ | Requirements gathering | Planning | Completed | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 11/27/2025 |  | 11/06/2025 | false | false | 01/06/2026 | UDAWELA U.K.R.M.R.N. it22271396
V9q_AmlczUKsyU8gpuKrIskAOyo4 | Presentation Preparation PP1 | Executing | Completed | Medium | MALSHAN W A D D I it22137050;WEERAWARDANE K W R C it22239402;UDAWELA U.K.R.M.R.N. it22271396;JAYASUNDARA K.B.S.M it22241832 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 11/01/2025 | 01/07/2026 | false | false | 01/06/2026 | UDAWELA U.K.R.M.R.N. it22271396 | Prepare proposal/presentation.
VxawsYtr3kiZGbPRjPVZ5ckAJhlK | Analyze Related Work in Fruits/Rice/Coffee Classification | Initiating | Completed | Low | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 08/10/2025 | 08/10/2025 | false | false | 11/19/2025 | WEERAWARDANE K W R C it22239402 | Compare similar AI-based grading solutions.
X7tUvd-43EqMFrLp_SSwUskAFsez | Connected Raspberry Pi to laptop via Ethernet & SSH | Executing | Completed | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 01/02/2026 | 12/19/2025 | 12/26/2025 | false | false | 01/02/2026 | WEERAWARDANE K W R C it22239402
Z6vjTrwhrEKQMsFwWWs9-MkAI0n4 | Data quality monitoring | Monitoring and controlling | Completed | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 11/27/2025 |  |  | false | false | 01/06/2026 | UDAWELA U.K.R.M.R.N. it22271396
_BMU5NcpN02nFNk6EBr3K8kAKY7e | Update GitHub reop and readme file | Planning | Completed | Important | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 11/01/2025 | 11/01/2025 | false | false | 11/19/2025 | WEERAWARDANE K W R C it22239402
bOSV3QUCr0a75imlO47w58kAJn5h | Identify Knowledge Gap in Existing Grading Methods | Initiating | Completed | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 08/10/2025 | 08/10/2025 | false | false | 11/19/2025 | WEERAWARDANE K W R C it22239402 | Identify issues in manual tea grading.
dophU0lZB0CoB7_jQBLfHMkAJl7n | Select Environmental Sensors (DHT22, Camera Module) | Planning | Completed | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 11/19/2025 | 12/06/2025 | false | false | 12/15/2025 | WEERAWARDANE K W R C it22239402 | Select IoT sensors.
fb2BreJLRU-_nytSvc-hBckAEZsu | Collect fertilization history data set through the field visit | Executing | Completed | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 11/27/2025 |  |  | false | false | 11/27/2025 | UDAWELA U.K.R.M.R.N. it22271396
j-xxB0m6LkyQXvB0X2iwPckAAdLD | Prepare Requirement Specification Document | Planning | Completed | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 08/30/2025 | 08/30/2025 | false | false | 11/19/2025 | WEERAWARDANE K W R C it22239402 | Create technical and functional requirements specification.
k8q4ogF89k6B70sF_4xP0ckAG9vv | Progress Presentation 01 | Closing | Completed | Medium | MALSHAN W A D D I it22137050;WEERAWARDANE K W R C it22239402;UDAWELA U.K.R.M.R.N. it22271396;JAYASUNDARA K.B.S.M it22241832 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  |  | false | false | 11/19/2025 | WEERAWARDANE K W R C it22239402 | Done the presentation part 01
o__RZb8fAE-SjdaSp5WRZMkAJqF4 | Monitor model performance | Monitoring and controlling | Completed | Medium | MALSHAN W A D D I it22137050 | MALSHAN W A D D I it22137050 | 11/27/2025 |  |  | false | false | 01/06/2026 | MALSHAN W A D D I it22137050
o_gCJQnvLUOC5hZ3puAweskAOflZ | Update MS Planner Progress Weekly | Monitoring and controlling | Completed | Low | MALSHAN W A D D I it22137050;WEERAWARDANE K W R C it22239402;UDAWELA U.K.R.M.R.N. it22271396;JAYASUNDARA K.B.S.M it22241832 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  |  | false | false | 01/04/2026 | JAYASUNDARA K.B.S.M it22241832 | Update progress.
owouuGEzAU6jnivS4dtoY8kAEwWl | Review existing apps like Plantix and Agrio | Initiating | Completed | Medium | MALSHAN W A D D I it22137050 | MALSHAN W A D D I it22137050 | 11/27/2025 |  |  | false | false | 01/06/2026 | MALSHAN W A D D I it22137050
qqBCv2YwDkyEhWBDFJFzNskAPKnw | Designed system architecture (IoT → Backend → Dashboard) | Planning | Completed | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 01/02/2026 | 12/19/2025 | 12/29/2025 | false | false | 01/02/2026 | WEERAWARDANE K W R C it22239402 | Design a 3D model to understand what the final product is actually was
sh30wvBOcE-v_WpKsL4nc8kADbzl | Research paper feedback and project discussion meeting with Supervisor and the Co- Supervisor | Planning | Completed | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 08/30/2025 | 09/10/2025 | false | false | 11/19/2025 | WEERAWARDANE K W R C it22239402
t52PgrkaY0GQbl2JqLF6lckAMpu3 | Prepare initial UI/UX design | Planning | Completed | Medium | MALSHAN W A D D I it22137050 | MALSHAN W A D D I it22137050 | 11/27/2025 |  |  | false | false | 01/06/2026 | MALSHAN W A D D I it22137050
t8LKfFuaLEqikeWXT5f88ckALcB5 | Define project scope and objectives | Planning | Completed | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 11/27/2025 |  |  | false | false | 01/06/2026 | UDAWELA U.K.R.M.R.N. it22271396
tV_iJfRRKE26-wWNYn6uK8kAB2O9 | Identify IoT requirements | Initiating | Completed | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 11/27/2025 |  |  | false | false | 11/27/2025 | UDAWELA U.K.R.M.R.N. it22271396
7T48KaeKwkajBGRejuMXsMkAK-6Z | PP1 Presentation | Closing | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
2qofK4ehrkq2hWMJnp6fIskAEwQR | Validate prediction accuracy against actual market prices | Monitoring and controlling | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
tAcTDYX_P0OCKE5Tzf9ozskAEmiW | Track data quality and handle missing or inconsistent data | Monitoring and controlling | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
4k2c15xv5E-bimD514tckckAEfQk | Tune hyperparameters and apply early stopping to prevent overfitting | Monitoring and controlling | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
Paox040hDUK7BS7FUY35i8kACcLC | Monitor model performance using predefined evaluation metrics | Monitoring and controlling | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
SaTBEulEyUO-aV8FeJLC18kAKc7o | Develop risk indicators based on price volatility | Executing | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
G7H3CBT-70eywCrKJtRkUckAFvnJ | Implement Histogram-Based Gradient Boosting regression model | Executing | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
jmfYZ3CEwEWdLp0i90TSLckAJnRR | Train and validate the tea price prediction model | Executing | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
KI3uCUxhl0q0Hru92OaD5ckAM4KT | Collect and preprocess historical and real-time tea market data | Executing | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
BXk89z8Ihk-szMf22Tm37skANLRF | Perform time-series feature engineering | Executing | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
WSvwStWwS0qw0MYpZusIP8kAOHSx | Select model approach (Time Series + Histogram-Based Gradient Boosting) | Planning | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
2x3Bh4NldE-Ds9AvNbFOHckAEAg5 | Identify and finalize required datasets (tea prices, climate, market data) | Planning | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
xXUueUmyskaCesaLK02CBskAGirr | Plan feature engineering strategy for supply, demand, and external factors | Planning | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
xDGhZXrAJUaQIQ5mQ7lxFskAKssp | Define system architecture for mobile app integration | Planning | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
eB7OAT0ic0CM7ha5QJAjIMkANAHK | Prepare detailed task schedule and milestone plan | Planning | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
QWElrjdMvEmjPENqub0FjMkABdmm | Identify the research problem in the Sri Lankan tea market | Initiating | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
JIhaZVXuNk2UwFa9-jO3TckALErd | Identify key stakeholders (tea sellers, exporters, researchers) | Initiating | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
wo2CrZFYMkKaXNUm-EB8tckAFMYr | Define the scope of the AI-based price forecasting component | Initiating | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
Qq7ulojJ5Eqx65G7FkdrHMkAIGoD | Define high-level objectives and expected outcomes | Initiating | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
p6zwOeh2ukiXXLHsTFofHskAFkgV | Conduct a preliminary feasibility analysis of AI/ML applicability | Initiating | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
WsB2YKVvmEOvjWpc6zByd8kAE5Gx | Obtain approval for the individual component within the group project | Initiating | Completed | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false | 01/11/2026 | JAYASUNDARA K.B.S.M it22241832
5WehFUL7kU-ht_f38f42V8kAM0c5 | Annotate Dataset | Planning | In progress | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 01/07/2026 |  | false | false |  |  | Annotate images for training.
8jbkizw4I0e_Bly1f_4JCskAAYb6 | Verified system runs continuously without crashing | Monitoring and controlling | In progress | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 01/02/2026 | 12/30/2025 |  | false | false
9WgOLixLKE-Sgo2CYG8Dy8kAEAcW | Split Dataset Into Training and Testing | Planning | In progress | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 01/14/2026 |  | false | false |  |  | Create dataset splits.
DxIaff-3XUS-a_ROU4YPNskANTbP | Design Backend Architecture | Planning | In progress | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 12/30/2025 |  | false | false |  |  | Plan server, API, and database design.
JYK0hNMvvUSN6RsMcdgk5skAM8wR | Organize and Label Dataset | Planning | In progress | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 01/10/2026 |  | false | false |  |  | Organize dataset folders and labels.
JaSOhkBTVEuXG4AtPmOFHckANKKT | Prepare Dataset Preprocessing Steps | Planning | In progress | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 01/11/2026 |  | false | false |  |  | Plan preprocessing workflow.
Mnt3mtGnw02J2Foo_07T78kAPO5E | Write Firmware to Capture Sensor Readings | Executing | In progress | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 01/11/2026 |  | false | false |  |  | Develop firmware.
Nl9AVW6QNUOGPUp-QPCiockAGnDG | Collect Tea Leaf Images Dataset | Executing | In progress | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 01/12/2026 |  | false | false |  |  | Collect dataset from field visit.
O64lhtq1aEmFBlpwfznZ_skAHwPI | Documentation & Final Report Writing | Closing | In progress | Medium | MALSHAN W A D D I it22137050;WEERAWARDANE K W R C it22239402;UDAWELA U.K.R.M.R.N. it22271396;JAYASUNDARA K.B.S.M it22241832 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  |  | false | false | 11/19/2025 |  | Prepare report.
SwHNUdIhn0ekOVsWWY1tV8kAPmT9 | Capture Tea Leaf Images Under Controlled Lighting | Executing | In progress | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 01/14/2026 |  | false | false |  |  | Capture images using standard lighting.
UOSgKgCRlkS0if3BYw2acckABHfu | Design CNN Model Architecture | Planning | In progress | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 11/22/2025 |  | false | false |  |  | Design model architecture for classification.
UYb9IaEcwEWXTkExcAnSXckACSQl | Connect IoT Device to Backend | Executing | In progress | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 12/24/2025 |  | false | false |  |  | Integrate IoT connection.
UtuBmP6uzEuMp4PbAgjgIMkABlzA | Evaluate Accuracy, Speed, Reliability | Monitoring and controlling | In progress | Medium | MALSHAN W A D D I it22137050;WEERAWARDANE K W R C it22239402;UDAWELA U.K.R.M.R.N. it22271396;JAYASUNDARA K.B.S.M it22241832 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 01/11/2026 |  | false | false |  |  | Check performance metrics.
XzdXGgogNEi88LPbWKSViskALRXo | Connect the Database | Planning | In progress | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  |  | false | false
bYM47eYFtEqdjO28QrzmVMkAPEAy | Report monthly status | Monitoring and controlling | In progress | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  | 03/08/2026 | true | false
hJG0T5i2P0-0FrDd6j9w9ckAF-e7 | Prepare Presentation Slides PP2 | Closing | In progress | Medium | MALSHAN W A D D I it22137050;WEERAWARDANE K W R C it22239402;UDAWELA U.K.R.M.R.N. it22271396;JAYASUNDARA K.B.S.M it22241832 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 11/19/2025 |  | false | false | 01/04/2026
nUKTgfQPXk6dlZMsraLmEskALeXG | Preprocess Images (Resize, Clean, Enhance) | Executing | In progress | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 01/11/2026 |  | false | false |  |  | Apply preprocessing using OpenCV.
oJ1zcLi-2Ei9SSULYRKpSMkAAkLE | Merge Individual Branches | Planning | In progress | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  |  | false | false
s4Ki0A8Y0UOLXdx7AOa-2skAIy5c | Collect Feedback From Tea Experts | Monitoring and controlling | In progress | Low | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 12/02/2025 |  | false | false |  |  | Gather feedback.
y_SwAWL1e0WoLLzoVTgxuckAF00s | Implement Real-Time Monitoring Dashboard | Executing | In progress | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 | 01/11/2026 |  | false | false |  |  | Create dashboard UI.
20a449DuSUOYYAg9w8EUDskAGncu | Conduct team performance reviews | Monitoring and controlling | Not started | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  | 09/08/2027 | false | false | 11/19/2025
2Zgchz_SKEaMN6oot_khKskAKJjx | Build API for Image Upload and Sensor Data | Executing | Not started | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  |  | false | false |  |  | Implement APIs.
5hYhT8xoMEmwUZ8he6mj1ckAGyLl | Cloud database setup | Executing | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 11/27/2025 |  | 01/12/2026 | false | false
7656Ibps_ke54VssTkRj1MkAGYAa | Train CNN Model With Dataset | Executing | Not started | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  |  | false | false |  |  | Train the model.
CUhgg3AkcEqu5ML0EsO6CskABFXk | Build CNN Model in TensorFlow/PyTorch | Executing | Not started | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  |  | false | false |  |  | Implement CNN model.
DRL0Oy3g3kmqk39BPiVq4MkACBFh | Firmware development | Executing | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 11/27/2025 |  |  | false | false
KS7fEf-190CASYKfsYJixMkAMrCT | Conduct Integration Testing | Monitoring and controlling | Not started | Medium | MALSHAN W A D D I it22137050;WEERAWARDANE K W R C it22239402;UDAWELA U.K.R.M.R.N. it22271396;JAYASUNDARA K.B.S.M it22241832 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  | 01/31/2026 | false | false |  |  | Test system integrations.
NT_4_p8u8E6eg3hO4niAPskAEncN | Testing & Performance Evaluation | Monitoring and controlling | Not started | Medium | MALSHAN W A D D I it22137050;WEERAWARDANE K W R C it22239402;UDAWELA U.K.R.M.R.N. it22271396;JAYASUNDARA K.B.S.M it22241832 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  |  | false | false |  |  | Evaluate accuracy and performance. |  |  | Purple
NxTyIRFtzUCywtSOklL1DskAJ4HS | Display Grading Results & Environment Data | Executing | Not started | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  |  | false | false |  |  | Show insights.
PyPml8gwvESVvLII4xcXUMkAIiEq | Hardware assembly and wiring (NPK sensors and micro controllers | Executing | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 11/27/2025 |  | 01/20/2026 | false | false
QNi5PC2MZU2MrRnsTSlzuMkAG4QU | Prepare Final Documentation | Closing | Not started | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  |  | false | false
RaT0YeWF-kKFAlGstdQzSckADTeT | Procure components and sensors | Executing | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 11/27/2025 |  |  | false | false
aja_xEywTUurFJ8J-Yld9ckAKZHw | Integrate IoT Sensors With Microcontroller | Executing | Not started | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  |  | false | false |  |  | Connect sensors to ESP32/RPi.
buaa3JkUS06iqqvw4yzpqckAF5pz | Develop Data Transfer API | Executing | Not started | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  |  | false | false |  |  | Develop API endpoints.
byxwpHmRDk6JMtiB0bd5Z8kAO2Wf | Capture Red Rust, Potassium Deficiency, and healthy leaf samples | Executing | Not started | Medium | MALSHAN W A D D I it22137050 | MALSHAN W A D D I it22137050 | 11/27/2025 |  |  | false | false
dlRxMtnHQEyepjWuz1YRFskAO87f | Integrate backend with datasets | Executing | Not started | Medium | MALSHAN W A D D I it22137050;UDAWELA U.K.R.M.R.N. it22271396 | MALSHAN W A D D I it22137050 | 11/27/2025 |  |  | false | false
elCIMtNUF0aGwwvAQ_5LkckAC3Ky | Conduct team performance reviews | Monitoring and controlling | Not started | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  | 09/08/2028 | true | false
kUmYmu5eokS2WhCntuWaR8kAPIOC | Final system testing and validating | Closing | Not started | Medium | MALSHAN W A D D I it22137050;WEERAWARDANE K W R C it22239402;UDAWELA U.K.R.M.R.N. it22271396;JAYASUNDARA K.B.S.M it22241832 | UDAWELA U.K.R.M.R.N. it22271396 | 11/27/2025 |  |  | false | false
ltCw-_jN-0qustBvF8uOzMkAFLZy | Configure Sensors With Microcontroller | Executing | Not started | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  |  | false | false |  |  | Set up hardware.
n_Ah0jZYVEC2v2M3L7HQQskAJ4Zy | System performance tracking | Monitoring and controlling | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 11/27/2025 |  |  | false | false
q4RQnHhVIkyk9sNfeWCYEMkAI1ri | Preprocess Dataset (Resize, Normalize, Denoise) | Executing | Not started | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  |  | false | false |  |  | Perform dataset preprocessing.
qOFKISLCNUuuxywAOfvizckADxNs | Sensor calibration and testing | Monitoring and controlling | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 11/27/2025 |  |  | false | false
rQ9ttEZhsECmUL2g_sB_BskAFpDi | Save & Export Best-Performing Model | Executing | Not started | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  |  | false | false |  |  | Export model.
sg_Fn6LO6kqzJl3qHQczvMkAHBTw | Integration of fertilization algorithm | Executing | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 11/27/2025 |  | 01/12/2026 | false | false
tOLAoen85kqX577U2YKeGMkANpSP | Validate Model & Tune Hyperparameters | Executing | Not started | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  |  | false | false |  |  | Check validation accuracy.
uSc9i9UkQUOTD5d2eqBAfskABDsZ | Test Continuous IoT Data Streaming | Executing | Not started | Medium | WEERAWARDANE K W R C it22239402 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  |  | false | false |  |  | Test streaming.
vmwW7IdYwECY_5eMSIHnH8kAPFg6 | Prepare Final presentation | Planning | Not started | Important | MALSHAN W A D D I it22137050;WEERAWARDANE K W R C it22239402;UDAWELA U.K.R.M.R.N. it22271396;JAYASUNDARA K.B.S.M it22241832 | WEERAWARDANE K W R C it22239402 | 11/19/2025 |  | 01/28/2026 | false | false | 01/10/2026
RRUpybWgtEylbN-P4LrldskAHeuf | Deliver final presentation and demonstration of the component | Closing | Not started | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false
mXBxN1zUa0WZnZLy1nhstckAI0ca | Prepare and submit final technical and research documentation | Closing | Not started | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false
n46keJI5cUa7Pnsn93vE4ckAA5za | Validate final results and document model performance outcomes | Closing | Not started | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false
0IwmosP5tka_aV7nMgfOZ8kAFbkp | Complete integration testing of the AI component within the mobile application | Closing | Not started | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false
3E1VGOkyT02c4r_HwjuGTskALZni | Finalize and freeze the trained tea price forecasting model | Closing | Not started | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false
dwtwEkTMoEWNarcWD1LCwskADTg5 | Ensure alignment with research objectives and project timeline | Monitoring and controlling | Not started | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false
1VNpqfkTzUePOVDeIE8D8skABIFh | Review system outputs based on user feedback | Monitoring and controlling | Not started | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false
RLn7eEccskacMVFwp3bLq8kANqkX | Integrate the AI component with the mobile application backend | Executing | Not started | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false
EG7WyAmh4kqPjspahkDnpckAFtbR | Define model evaluation metrics (RMSE, MAE, R²) | Planning | Not started | Medium | JAYASUNDARA K.B.S.M it22241832 | JAYASUNDARA K.B.S.M it22241832 | 01/11/2026 |  |  | false | false
1NGFv8a5zUmJ0kgO_UfybskACa48 | Log and analyze failed sensor transmissions | Monitoring and controlling | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 01/11/2026 |  |  | false | false
roCe_ovAykSrW90AhR4SMckAI_Oq | Monitor model confidence scores | Monitoring and controlling | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 01/11/2026 |  |  | false | false
htVqizQmR0SKqZwlEddqlMkACLbb | Sustainability and future work recommendations | Closing | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 01/11/2026 |  |  | false | false
Tv7gFqr5Oku-iVi-6x3oF8kAEkmD | Model reproducibility verification | Closing | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 01/11/2026 |  |  | false | false
zUkUDKFHrU6McUnnZwy7LskAD4jX | Final dataset freeze & version tagging | Closing | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 01/11/2026 |  |  | false | false
ENgUEJNaN0Cp1Aghmdv898kALoOm | Track cloud resource utilization | Monitoring and controlling | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 01/11/2026 |  | 01/31/2026 | false | false
3f9FbCyt7EGH8FL3vf_qrMkAAr4p | Validate real-time vs stored data consistency | Monitoring and controlling | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 01/11/2026 |  | 01/20/2026 | false | false
2_e0mXIA7kWZR4Exk4orJMkAKKxA | Monitor sensor drift over time | Monitoring and controlling | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 01/11/2026 |  | 01/20/2026 | false | false
nQXwOR0wBUWtowsOErDuL8kAJklf | Optimize ML inference for low-latency use | Executing | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 01/11/2026 |  | 01/14/2026 | false | false
S4w4XKh5-EOyja4C0LnBTskAM3ad | Create automated data labeling process | Executing | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 01/11/2026 |  | 01/18/2026 | false | false
YIu4ZM-I0UyF561AP8-uackABWBU | Integrate weather API with soil data | Executing | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 01/11/2026 |  |  | false | false
eEMtaLkkGUqV4lIUt0QFmskADY0J | Develop data normalization pipeline | Executing | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 01/11/2026 |  | 01/16/2026 | false | false
LdN1Q3r4o0215O1QNuCZEckANHE3 | Implement sensor fault detection logic | Executing | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 01/11/2026 |  | 01/15/2026 | false | false
0kPpDByPdk-yUicijzBhMskAAJEi | Prepare ethical approval / consent workflow | Planning | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 01/11/2026 |  | 01/18/2026 | false | false
ZciloLwMnUiweFcJ0sEk5skABkOr | Select communication protocol (MQTT vs HTTP) | Planning | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 01/11/2026 |  | 01/17/2026 | false | false
_B7SnPjrlk6bx8gXqw4KB8kAG1Ng | Define alert thresholds for soil parameters | Planning | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 01/11/2026 |  | 01/16/2026 | false | false
J9CaeIDvs0qlGg74riHaY8kAC7Yl | Plan offline data capture strategy | Planning | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 01/11/2026 |  | 01/15/2026 | false | false
k-NxCHKnqECGX76smA0i5MkAAy7l | Create sensor calibration schedule | Planning | Not started | Medium | UDAWELA U.K.R.M.R.N. it22271396 | UDAWELA U.K.R.M.R.N. it22271396 | 01/11/2026 |  | 01/14/2026 | false | false

## Plan name
Plan name | Tea Vision 360
Plan ID | HPDVTzB11E-AwPyVMHXUkckAH-Yc
Date of export | 01/11/2026